## Changes
Short Description | Long Description | Change Type | Change Category | Implementation Steps | Validation Steps | Rollback Plan | Planned Window | Impacted Services | Complexity | Long description
Update nginx worker process count to 8 | Setting worker_processes to 8 to better utilize 8-core CPU resources based on load testing results | standard | configuration | 1. SSH to prod-web-01 2. Edit /etc/nginx/nginx.conf: worker_processes 8 3. Test config: nginx -t 4. Reload: systemctl reload nginx 5. Monitor /var/log/nginx/error.log | 1. Check processes: ps aux ¦ grep nginx 2. Load test with 1000 req/sec 3. Monitor CPU utilization 4. Check response times | 1. Revert nginx.conf to worker_processes 4 2. Test: nginx -t 3. Reload nginx 4. Verify with load test | 2024-02-20T23:00:00Z | Web Server | low
Add read-only database user for analytics team | Creating new database user with SELECT-only privileges for analytics team to run queries on production database without risk of modifications | standard | configuration | 1. Connect to MySQL master 2. Run: CREATE USER 'analytics_ro'@'%' IDENTIFIED BY '[secure_password]' 3. GRANT SELECT ON database.* TO 'analytics_ro'@'%' 4. FLUSH PRIVILEGES 5. Test with analytics team credentials | 1. Verify user created: SELECT user FROM mysql.user 2. Test SELECT query works 3. Verify INSERT/UPDATE fails 4. Document in access control sheet | 1. DROP USER 'analytics_ro'@'%' 2. FLUSH PRIVILEGES 3. Verify access removed | 2024-02-21T10:00:00Z | Database | low
Update DNS A record for new IP address | DNS record for api.company.com needs to point to new load balancer IP 203.0.113.45 after infrastructure migration | standard | configuration | 1. Access DNS management console 2. Update A record api.company.com 3. Old IP: 192.0.2.50 4. New IP: 203.0.113.45 5. Set TTL to 300 seconds 6. Apply changes | 1. Query DNS: nslookup api.company.com 2. Verify resolution to new IP 3. Monitor for 10 minutes 4. Check load balancer health | 1. Revert A record to 192.0.2.50 2. Set TTL to 300 3. Monitor connectivity | 2024-02-22T22:00:00Z | API Gateway, Load Balancer | low
Enable gzip compression in web server | Enable gzip compression for HTTP responses to reduce bandwidth usage. Compression tested with various file types. | standard | configuration | 1. SSH to web servers 2. Edit /etc/apache2/mods-available/deflate.conf 3. Enable: a2enmod deflate 4. Restart Apache: systemctl restart apache2 5. Verify in headers | 1. Check header: curl -I http://localhost ¦ grep -i encoding 2. Test page size reduction: curl ¦ wc -c 3. Load test performance 4. Browser verification | 1. a2dismod deflate 2. systemctl restart apache2 3. Verify non-compressed responses | 2024-02-23T03:00:00Z | Web Server, CDN | low
Deploy API v2.1.0 with user profile endpoint | Deploying new API v2.1.0 containing new user profile endpoint with improved caching strategy. Tested in staging for 1 week. | normal | deployment | 1. Pull release v2.1.0 from registry 2. Blue-green deployment: deploy to green env 3. Run smoke tests 4. Switch traffic: haproxy reload 5. Monitor green environment 6. Blue kept as rollback | 1. Health checks on new endpoints 2. Load test: 2000 req/sec for 10 min 3. Check error rates vs baseline 4. Verify latency within SLA 5. Monitor CPU/memory usage | 1. Detect issue in canary (5% traffic) 2. Switch traffic back to v2.0.5 3. Investigate in green environment 4. Roll forward with fix after 24 hours | 2024-02-20T22:00:00Z | API Gateway, API Service, User Database, Cache | medium
Database query optimization for user listings | Adding index on users.email column to improve query performance for user lookups. Query currently takes 2 seconds for 1M users, should reduce to <100ms. | normal | database | 1. Backup users table 2. ANALYZE TABLE users 3. CREATE INDEX idx_email ON users(email) 4. Monitor slow query log 5. Update query execution plan | 1. Query explain plan shows index usage 2. Run SHOW INDEX from users 3. Benchmark query: SELECT ... WHERE email='test@example.com' 4. Performance should be <100ms | 1. DROP INDEX idx_email ON users 2. Run ANALYZE TABLE users again 3. Verify performance reverted | 2024-02-21T02:00:00Z | Database, User Service | medium
Scale Redis cache cluster to 5 nodes | Increase Redis cluster from 3 to 5 nodes to handle 50% higher traffic load forecasted for Q2. Current node at 80% capacity. | normal | infrastructure | 1. Provision 2 new Redis instances 2. Config: redis.conf with cluster mode 3. Add nodes to cluster: CLUSTER MEET 4. Rebalance slots: CLUSTER SLOTS 5. Monitor memory usage 6. Enable persistence monitoring | 1. Verify 5 nodes in cluster: CLUSTER NODES 2. Test with cache load 3. Monitor memory per node (<70%) 4. Test failover scenarios 5. Performance benchmark | 1. Remove new nodes from cluster 2. Rebalance to 3 nodes 3. Decommission new instances 4. Verify application connectivity | 2024-02-22T01:00:00Z | Cache, Search Service, Session Store | medium
Update SSL certificate for *.api.company.com | Renewing wildcard SSL certificate expiring in 7 days. New cert valid for 1 year. Zero-downtime update with HAProxy. | normal | infrastructure | 1. Generate new CSR for *.api.company.com 2. Obtain new certificate from CA 3. Copy new cert to /etc/ssl/certs/ 4. Update HAProxy config 5. HAProxy reload (graceful) 6. Verify cert in browser | 1. Check cert: openssl s_client -connect api.company.com:443 2. Verify expiry date 3. Check certificate chain 4. Browser validation (no warnings) 5. API endpoint verification | 1. Restore old cert file 2. HAProxy reload 3. Verify old cert active | 2024-02-20T20:00:00Z | API Gateway, Load Balancer, All API Services | medium
Migrate user data to MongoDB - Phase 1 | Phase 1 of user data migration from PostgreSQL to MongoDB. Includes user profiles, preferences. Data consistency checks required. No rollback tested. | normal | database | 1. Export user data from PostgreSQL 2. Transform to MongoDB format 3. Import to MongoDB cluster 4. Run sanity checks 5. Update application ORM | 1. Row count comparison 2. Data type verification 3. Query performance comparison 4. User session tests | Would require full data resync - not tested | 2024-02-25T00:00:00Z | Database, User Service, Authentication, Session Manager | high
Emergency hotfix: CRITICAL XSS vulnerability in profile editor | CRITICAL security issue discovered: User input not sanitized in profile bio field. Attacker can inject JavaScript affecting all users viewing the profile. | emergency | deployment | 1. Deploy hotfix v2.0.1 immediately 2. Apply input sanitization on bio field 3. Validate all profile endpoints 4. Clear cached profiles | 1. Attempt XSS payload injection - should be escaped 2. Verify profile display works 3. Check database for malicious content 4. Monitor error rates | 1. If critical issues, rollback to v2.0.0 2. Keep hotfix branch for investigation | 2024-02-19T14:30:00Z | API Service, Web Frontend, User Database | high
Backup system disk space cleanup - rm old logs | Backup partition at 95% capacity. Need to delete old application logs to free up space. | standard | configuration | 1. SSH to backup server 2. Run: rm -rf /backup/logs/2023/* 3. Run: df -h to verify space | Confirm disk space increased | None - data is gone | 2024-02-20T15:00:00Z | Backup System | low
Production database master failover test | Testing MySQL master-slave failover to ensure HA works. Switch production writes to replica and back. | normal | infrastructure | 1. Put old master in read-only mode 2. Promote replica to master 3. Update app connection strings 4. Run smoke tests 5. Demote old master to replica 6. Verify replication | 1. Verify writes go to new master 2. Check replication lag: SHOW SLAVE STATUS 3. Query all critical tables 4. Monitor for errors | Promote original master back if issues occur (tested previously) | 2024-02-21T04:00:00Z | Database, All Services Using DB | high
Update production configuration file |  | standard | configuration | Update config files | Test | Revert if needed | 2024-02-20T08:00:00Z | Multiple | medium | Some configuration updates needed in production
Payment processing system maintenance | Performing maintenance on critical payment system. Very critical but under-documented. | normal | infrastructure | 1. Perform maintenance 2. Restart service 3. Monitor | Check if it works | Restart if broken | 2024-02-21T10:00:00Z | Payment Gateway, Payment Service, Billing Database, Accounting System | high
Cache layer upgrade from Redis 5 to 6 | Redis version upgrade from 5.0 to 6.2 LTS. Major version change with new features. | normal | infrastructure | 1. Download Redis 6.2 2. Compile from source 3. Stop Redis 5 4. Change /etc/redis.conf to point to new binary 5. Start Redis 6.2 6. Check if keys migrated | 1. Check Redis version: redis-cli --version 2. Run some cache gets 3. Monitor | Switch back to /opt/redis-5/bin/redis-server | 2024-02-22T22:00:00Z | Cache, Session Store, Search Service | high
Add monitoring dashboard for API latency | Creating new Grafana dashboard to monitor P50, P95, P99 latencies for all API endpoints. Uses existing Prometheus metrics. | standard | configuration | 1. Access Grafana UI 2. Create new dashboard 3. Add panels for API latency queries 4. Save dashboard 5. Share with team | 1. Dashboard displays correctly 2. Metrics update in real-time 3. Alert rules functional | Delete dashboard from Grafana | 2024-02-20T12:00:00Z | Monitoring System | low
Deploy authentication service v3.0.0 | Major authentication service upgrade with OAuth 2.0 and MFA support. Extensively tested in staging for 3 weeks. | normal | deployment | 1. Deploy v3.0.0 to canary (5% users) 2. Monitor for errors for 30 min 3. Increase to 50% gradually 4. Full deployment after 2 hours 5. Keep v2.5.0 running for quick rollback | 1. Login functionality works 2. MFA enrollment works 3. OAuth providers functional 4. No auth service errors 5. Error rate <0.1% | Route traffic back to v2.5.0, send logs for investigation | 2024-02-23T23:00:00Z | Authentication Service, API Gateway, Web Frontend, Mobile App | high
Disable old deprecated API v1 endpoints | Disabling API v1 endpoints deprecated 6 months ago. All clients have migrated. Endpoints will return 410 Gone. | normal | deployment | 1. Update API gateway routing 2. Remove v1 route mappings 3. Add 410 responses for v1 4. Update documentation 5. Send to clients | 1. v1 endpoints return 410 2. v2 endpoints still work 3. No internal services use v1 4. Monitor for client complaints | Restore v1 routing if clients still using (unlikely) | 2024-02-24T00:00:00Z | API Gateway, External Clients | medium
ElasticSearch cluster upgrade 7.x to 8.x | Major ElasticSearch version upgrade. Major index format changes. 3-cluster setup, rolling upgrade strategy. | normal | infrastructure | 1. Upgrade node 1: systemctl stop elasticsearch 2. Install ES 8.x 3. systemctl start elasticsearch 4. Wait for cluster recovery 5. Repeat for node 2, 3 | 1. Check cluster health: green 2. Shard distribution correct 3. Index queries still work 4. No data loss | Downgrade nodes if critical issues found | 2024-02-25T02:00:00Z | Search, Logging, Analytics | high
Add Slack integration to incident alerts | Integrating PagerDuty with Slack to send incident alerts to #incidents channel. Webhook-based integration. | standard | configuration | 1. Create Slack webhook in channel settings 2. Configure PagerDuty integration 3. Test with sample alert 4. Enable for all incident types | 1. Trigger test incident 2. Verify Slack notification received 3. Check message formatting 4. Verify actionable info present | Disable Slack notification in PagerDuty | 2024-02-20T10:00:00Z | Incident Management, Slack Workspace | low
Infrastructure as Code migration to Terraform | Migrating from manual AWS CloudFormation to Terraform IaC. Large scope affecting all infrastructure. | normal | infrastructure | 1. Write Terraform modules for all components 2. Dry run: terraform plan 3. Stage environment first 4. Import existing AWS resources: terraform import 5. Gradually deploy to prod | 1. All resources created identically 2. No resources added/removed 3. Security groups correct 4. Network connectivity working | Keep CloudFormation running in parallel for 30 days | 2024-02-26T22:00:00Z | All Infrastructure, CI/CD Pipeline | high
Network switch firmware update | Critical network switch firmware update from 12.1 to 12.5. Resolves performance issues. | normal | infrastructure | 1. Download firmware 12.5 2. Backup current config 3. Reboot switch to boot new firmware 4. Verify all ports coming up 5. Run diagnostic tests | 1. All ports up and running 2. Throughput normal 3. Latency acceptable 4. No packet loss | Reboot with old firmware version | 2024-02-23T02:00:00Z | All Network Traffic | high
Kubernetes cluster upgrade to 1.29 | Kubernetes master/node upgrade from 1.27 to 1.29. 2-node cluster with in-place upgrade. | normal | infrastructure | 1. Drain node 1: kubectl drain node1 2. Upgrade kubelet and kubeadm 3. kubeadm upgrade node 4. Uncordon node 5. Repeat for node 2 | 1. All pods rescheduled successfully 2. Services still responsive 3. Storage volumes mounted 4. Check kubectl version | Downgrade nodes if cluster unstable | 2024-02-24T01:00:00Z | All Containerized Services | high
Update DNS failover for disaster recovery | Updating Route53 health checks and failover rules to account for new secondary data center. | standard | configuration | 1. Create health check for new data center API 2. Update Route53 record with failover policy 3. Set health check threshold 4. Test failover behavior 5. Monitor DNS resolution | 1. Resolve primary DC IP when healthy 2. Resolve secondary DC IP when primary unhealthy 3. Failover time <30 seconds 4. Both IPs accessible | Restore original Route53 config | 2024-02-21T20:00:00Z | DNS, Load Balancing, All Services | medium